## Requirements Inventory
Goal ID | SMART Goal | Requirement ID | Requirement Statement | Transaction (Input → Process → Output) | Type | Priority | Status Percenntage | Notes / Issues | Owner
G1 | Increase user registration completion rate from 70% to 90% within 6 months. | REQ-101 | The system shall allow one-click social media sign-up. | User clicks 'Sign Up with Google' → System requests Google OAuth token → User account created in database. | Functional | Must | 100% | Already integrated with Google OAuth
G1 | Increase user registration completion rate from 70% to 90% within 6 months. | REQ-102 | The system shall send automated onboarding emails within 5 minutes of registration. | New user registered → Email service triggers onboarding template → User receives welcome email. | Functional | Should | 80% | Template ready, automation pending
G2 | Reduce average page load time to ≤ 2 seconds for 95% of requests by Dec 2025. | REQ-201 | The system shall implement CDN-based static content delivery. | Browser requests static content → CDN serves cached content from nearest node → Page loads faster. | Non-functional | Must | 90% | CDN vendor shortlisted
G2 | Reduce average page load time to ≤ 2 seconds for 95% of requests by Dec 2025. | REQ-202 | Optimize images for web without quality loss. | Upload image → System compresses and stores optimized version → Serve optimized image on request. | Non-functional | Must | 100% | Compression library under review
G3 | Ensure 100% compliance with GDPR by Q1 2026. | REQ-301 | The system shall allow users to request data deletion. | User submits deletion request → System validates identity → Deletes personal data from all storage. | Functional | Must | 100% | Legal review complete
G4 | Achieve 24/7 service availability with ≤ 4 hours unplanned downtime per year. | REQ-401 | The system shall implement failover to a secondary server. | Primary server fails → Load balancer redirects traffic to backup → Service restored. | Non-functional | Must | 0% | Secondary server ready for testing
Note: | REQ-101 (Goal#¦Transaction#)

## Traceability Matrix
Requirement ID | SRS Reference (Use Cases, Activity Diagrams, Wireframes) | SDD Reference (Class Diagrams, Sequence Diagrams, User Innterfaces, Databases) | Implemenntation Module(s)/Component(s) | STD Reference (Test Case IDs) | Status
REQ-101 | UC-101, AD-101, WF-101 | CD-101, SD-101, UI-101, DB-101 | signup_controller.py, oauth_service.py | TC-101, TC-102 | Passed
REQ-102 | UC-102, AD-102, WF-102 | CD-102, SD-102, UI-102, DB-102 | email_service.py | TC-103 | Pending
REQ-201 | UC-201, AD-201, WF-201 |  | cdn_config.yaml | TC-201, TC-202 | In Progress
REQ-202 |  |  | image_service.py | TC-203 | Not Started
REQ-301 |  |  | data_deletion_service.py | TC-301 | Pending
REQ-401 |  |  | failover_manager.py | TC-401, TC-402 | In Progress